## Sprint
[5 empty] | Start Date | 2024-02-15 |  |  | 2024-02-15 |  |  | 2024-02-16 |  |  | 2024-02-17 |  |  | 2024-02-18 |  |  | 2024-02-19 |  |  | 2024-02-20 |  |  | 2024-02-21 |  |  | 2024-02-22 |  |  | 2024-02-23 |  |  | 2024-02-24 |  |  | 2024-02-25 |  |  | 2024-02-26 |  |  | 2024-02-27 |  |  | 2024-02-28 |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF!
[10 empty] | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 |  |  | Day 5 |  |  | Day 6 |  |  | Day 7 |  |  | Day 8 |  |  | Day 9 |  |  | Day 10 |  |  | Day 11 |  |  | Day 12 |  |  | Day 13 |  |  | Day 14 |  |  | Day 31 |  |  | Day 32 |  |  | Day 33 |  |  | Day 34 |  |  | Day 35 |  |  | Day 36 |  |  | Day 37 |  |  | Day 38 |  |  | Day 39 |  |  | Day 40
Worktype | Deliverable Area | Product Backlog Item or Group | Work item ID | Sprint Work item Description | Driver | Status | Pri | Initial | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Total Effort
Story / Feature | Coding | Product Backlog | 1 | user story 1 - plot owner logged in (sprint 1) | agreeran01@qub.ac.uk | complete | 3 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0.5 | 2.5 | In Progress | 0 | 2.5 | In Progress | 0 | 2.5 | In Progress | 1 | 1.5 | In Progress | 0 | 1.5 | In Progress | 1 | 0.5 | In Progress | 0.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 3
Story / Feature | Coding | Product Backlog | 2 | user story 2 - admin passwords (sprint 1) | phepden01@qub.ac.uk | complete | 1 | 1 | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 1
Story / Feature | Coding | Product Backlog | 3 | user story 3 - selecting veg to plant (sprint 1) | agreeran01@qub.ac.uk | complete | 2.5 | 2.5 | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 2.5 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 2.5
Story / Feature | Coding | Product Backlog | 4 | user story 4 - view details on the growth of the crop(sprint 1) | scameronleckey02@qub.ac.uk | complete | 4 | 4 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 2 | 1 | In Progress | 0 | 1 | In Progress | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 4
Story / Feature | Coding | Product Backlog | 5 | user story 5 - view details on the crops' water level (sprint 1) | scameronleckey02@qub.ac.uk | complete | 2 | 4 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 2
Story / Feature | Coding | Product Backlog | 6 | user story 6 - track when crops are watered (sprint 1) | hdennis02@qub.ac.uk | complete | 1 | 1 | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 1 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 1
Story / Feature | Coding | Product Backlog | 7 | user story 8 - admin overview of plots (sprint 1) | phepden01@qub.ac.uk | complete | 5 | 4 | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 1 | 3 | In Progress | 2 | 1 | In Progress | 2 | 0 | Complete | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 6
Story / Feature | Coding | Product Backlog | 8 | user story 9 - view user details (sprint 1) | phepden01@qub.ac.uk | complete | 3 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 2
Precondition / Debt | Coding |  | 9 | coding the plot owner class | agreeran01@qub.ac.uk | complete | 5 | 5 | 2 | 3 | In Progress | 0.5 | 2.5 | In Progress | 1 | 1.5 | In Progress | 0 | 1.5 | In Progress | 0.5 | 1 | In Progress | 0 | 1 | In Progress | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 5
Precondition / Debt | Coding |  | 10 | coding the admin class | lmccall09@qub.ac.uk | Complete | 4 | 4 | 0 | 4 | Pending | 1 | 3 | In Progress | 0 | 3 | In Progress | 0 | 3 | In Progress | 2 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 4
Precondition / Debt | Coding |  | 11 | coding tbe crop class | scameronleckey02@qub.ac.uk | complete | 5 | 7 | 2 | 3 | In Progress | 0 | 3 | In Progress | 0.5 | 2.5 | In Progress | 0 | 2.5 | In Progress | 0 | 2.5 | In Progress | 0 | 2.5 | In Progress | 0 | 2.5 | In Progress | 2 | 0.5 | In Progress | 0.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 5
Precondition / Debt | Coding |  | 12 | organise file structiure and method to add and remove | hdennis02@qub.ac.uk | Complete | 8 | 8 | 0 | 8 | Pending | 0 | 8 | Pending | 0 | 8 | Pending | 0 | 8 | Pending | 0 | 8 | Pending | 0 | 8 | Pending | 4 | 4 | In Progress | 3 | 1 | In Progress | 0 | 1 | In Progress | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 8
Precondition / Debt | Coding |  | 13 | coding plot class | hdennis02@qub.ac.uk | Complete | 2 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 2
Precondition / Debt | Coding |  | 14 | organising classes for file access and finishing touches | hdennis02@qub.ac.uk | Complete | 3 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 3 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 3
Precondition / Debt | Coding |  | 15 | writing tests for classes | lmccall09@qub.ac.uk | Pending | 1 | 4 | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0
Precondition / Debt | Coding |  | 10 | coding the admin class | phepden01@qub.ac.uk | complete | 4 | 7 | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 1 | 6 | In Progress | 2 | 4 | In Progress | 1 | 3 | In Progress | 0 | 3 | In Progress | 0 | 3 | In Progress | 4 | 0 | Complete | 0 | 0 | Complete | 1 | 0 | Complete | 0 | 0 | Complete | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 9
0
[9 empty] | Day |  | 1 | Day |  | 2 | Day |  | 3 | Day |  | 4 | Day |  | 5 | Day |  | 6 | Day |  | 7 | Day |  | 8 | Day |  | 9 | Day |  | 10 | Day |  | 11 | Day |  | 12 | Day |  | 13 | Day |  | 14 | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF! | Day |  | #REF!
|  |  |  | Time Spent Mask |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
|  |  |  | Time Left Mask |  |  |  |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0
|  |  |  | Status Mask |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
300 | 300 | 300 | 56A | Totals |  |  |  | 61.5 | 4 | 52.5 |  | 1.5 | 51 |  | 2 | 49 |  | 0 | 49 |  | 2.5 | 46.5 |  | 6 | 40.5 |  | 7 | 33.5 |  | 16 | 18.5 |  | 5 | 13.5 |  | 3 | 11.5 |  | 6 | 7.5 |  | 0 | 7.5 |  | 3.5 | 5 |  | 1 | 4 |  | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF!
Note on AQ19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sadly peter's work bugged and had to be reverted; so he had to restart

## Analysis
Calendar Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Date |  | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28
Total Hours Remaining |  | 52.5 | 51 | 49 | 49 | 46.5 | 40.5 | 33.5 | 18.5 | 13.5 | 11.5 | 7.5 | 7.5 | 5 | 4
Hours Worked Today |  | 0 | 1.5 | 2 | 0 | 2.5 | 6 | 7 | 16 | 5 | 3 | 6 | 0 | 3.5 | 1
Total Hours Worked To Date |  | 0 | 1.5 | 3.5 | 3.5 | 6 | 12 | 19 | 35 | 40 | 43 | 49 | 49 | 52.5 | 53.5
Total Worked & Remaining Hours |  | 52.5 | 52.5 | 52.5 | 52.5 | 52.5 | 52.5 | 52.5 | 53.5 | 53.5 | 54.5 | 56.5 | 56.5 | 57.5 | 57.5
Average Hours Worked Per Day |  | 0 | 0.75 | 1.1667 | 0.875 | 1.2 | 2 | 2.7143 | 4.375 | 4.4444 | 4.3 | 4.4545 | 4.0833 | 4.0385 | 3.8214
Estimated Completion Date (Burndown) |  | 2024-02-15 | 2024-04-24 | 2024-03-30 | 2024-04-14 | 2024-03-28 18:00 | 2024-03-11 06:00 | 2024-03-04 08:13 | 2024-02-26 05:29 | 2024-02-26 00:54 | 2024-02-26 16:11 | 2024-02-26 16:24 | 2024-02-27 20:05 | 2024-02-28 05:43 | 2024-02-29 01:07
Estimated Completion Date (Task Completion) |  | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-07-20 12:00 | 2024-04-06 12:00 | 2024-03-06 09:36 | 2024-03-01 01:12 | 2024-02-26 09:16 | 2024-02-25 12:13 | 2024-02-26 13:20 | 2024-02-27 05:31 | 2024-02-28
Task Hours Pending |  | 46.5 | 42.5 | 39.5 | 39.5 | 39.5 | 27.5 | 19.5 | 10.5 | 8.5 | 8.5 | 7.5 | 7.5 | 5 | 4
Task Hours In Progress |  | 6 | 10 | 13 | 13 | 13 | 23 | 26 | 23 | 15 | 2 | -5 | -5 | -4 | -4
Task Hours Complete |  | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 20 | 30 | 44 | 54 | 54 | 56.5 | 57.5
Count of Workitems Pending |  | 14 | 13 | 12 | 12 | 12 | 9 | 8 | 5 | 4 | 4 | 3 | 3 | 2 | 1
Count of Workitems In Progress |  | 2 | 3 | 4 | 4 | 4 | 6 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0
Count of Workitems Complete |  | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 6 | 9 | 11 | 13 | 13 | 14 | 15
Workbook Settings |  | 2024-02-17: Comments
| SkipWeekends | 2024-02-15: 0; 2024-02-17: (0=30 calendar days; 1=30 working days). Set to 1 to have dates skip over weekends (30 working day sprint, >30 calendar day sprint). Do not switch after Sprint has started or data will be stored under wrong days
| DailyScrumDateModifier | 2024-02-15: 0; 2024-02-17: Number of days added to or subtracted from today's date to ensure the highlighted date column in the sprint worksheet corresponds to the day of the current daily Scrum meeting
Workbook-Wide Constants
| BurndownColumns | 2024-02-15: 3
HoursSpentColumn | bar: 2024-02-15
| HoursLeftColumn | 2024-02-15: 2
| StatusColumn | 2024-02-15: 3
Note on I23: Mitch Lacey: Rocky in class this day
Note on E41: Negative number to go back from today's date; positive number to go forward from today's date.

## Capacity
Current Date |  | Thu | 2024-02-29
Sprint Start Date |  | Thu | 2024-02-15
Sprint Tracking Statistics
Productive Hours = | 35 |  | Sprint Days = | 20 |  | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25
|  |  | Scrum Team | %age of time on Project | Assigned Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | Available Hours
Total Remaining Hours: | 4 |  | scameronleckey02@qub.ac.uk | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 28
Total Capacity in Hours: | 140 |  | agreeran01@qub.ac.uk | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 28
Variance in Hours: | -136 |  | hdennis02@qub.ac.uk | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1 |  |  | 28
|  |  | phepden01@qub.ac.uk | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 28
|  |  | lmccall09@qub.ac.uk | 100% | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 28
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[6 empty] | v | = | Vacation & Public Holiday | [5 empty] | h | = | OOF (Sick, Biz Travel etc.)

## Team Roster
Sprint Vision: | To make the foundation of our community gardening centre
Sprint Team | Name | Alias | Primary Phone | Mobile Phone | Alternate Email | Instant Messaging
.
| Simon Leckey | scameronleckey02@qub.ac.uk | Phone | 7740038593 | simonleckey@outlook.com | IM Information
| Adam Greeran | agreeran01@qub.ac.uk | Phone | 7533244400 | a.greeran11@gmail.com | IM Information
| Hannah Dennis | hdennis02@qub.ac.uk | Phone | 7490814418 | Hannahaedennis@gmail.com | IM Information
| Peter Hepden | phepden01@qub.ac.uk | Phone | 7534720369 | Peterhepden@outlook.com | IM Information
| Luke Mccall | lmccall09@qub.ac.uk | 7495499119 | 7495499119 | luke.mccall03@gmail.com | IM Information

## Project Specific Reports
Work Type Breakdown
Story / Feature | 0 | #DIV/0!
Tax | 0 | #DIV/0!
Precondition / Debt | 0 | #DIV/0!
Spike | 0 | #DIV/0!
Total | 0 | #DIV/0!
Functional Breakdown
Coding | 0 | #DIV/0!
Documentation | 0 | #DIV/0!
Testing | 0 | #DIV/0!
Project Mgt | 0 | #DIV/0!
Total | 0 | #DIV/0!
Work Item Status
Complete | 15 | 93.75%
In Progress | 0 | 0%
Pending | 1 | 6.25%
Postponed | 0 | 0%
Cancelled | 0 | 0%
Total | 16 | 100%