## ProductBacklogTemplate
Team Number/Name: |  |  | 4
ID | Name | As a/an | I want to … | so that … | Notes | Sprint | Story Points | Assigned to | Dependencies | Status | Priority | Acceptance Test 1 | Acceptance Test 2 | Acceptance Test 3
Unique ID for the Story | Short Descriptive Name for the Story | As a <user> | I want <feature> | So that <reason> | Add any information here needed to remind each team member of the details | Indicate the Sprint this Story will be implemented in |  | Which team member(s) is this assigned to? | Which stories must be done prior to this? | Is this Story not started, in progress, done? | Is this story High, Medium or Low priority? | Given … when … then | Given … when … then | Given … when … then
1 | plot owner log in | plot owner | be able to log in to my account | to keep track of my personal crops and plots |  | 1 | 3 hours | Adam | / | Done | High | given correct details when logging in, i have access to the correct account | given incorrect details when logging in, I am denied access to my account
2 | admin password | admin | be able to enter a password for admin access | to ensure no unauthorised access to admin features |  | 1 | 1 hour | Peter | / | Done | High | given correct details when logging in, i have access to the admin account | given incorrect details when logging in, I am denied access to admin account
3 | choosing vegetable | plot owner | i would like to select what veg to plant | i can grow the crops i need thus saving money and time |  | 1 | 3 hours | Adam | 1 | Done | High | selected veg appears in plot owners plot
4 | current growth stage | plot owner | view details on the growth of the current crop | i can keep track of growth stage | paired programming? | 1 | 4 hours | Simon | 3 | Done | High | details of the crop are shown
5 | check water level | plot owner | view details on the water level of the current crop | i can water it when needed | paired programming? | 1 | 2 hours | Simon | 3 | Done | High | details of the crop's water level are shown
6 | water plants (update how much and when) | plot owner | to track when crops are watered | i can reset the watering time |  | 1 | 1 hour | Hannah | 5 | Done | High | given i track watering, current items watering level is reset to zero
7 | rain tracking | plot owner | to track when it rains | to reset all watering times for crops |  | 2 | 3 hours | Hannah | 6 | Done | High | given i track rain, all items watering levels are reset to zero
8 | admin overview | admin | overview of all plots and contents | admin can organise garden |  | 1 | 5 hours | Peter | / | Done | Medium | displays the plotowner, when they planted it and what they planted
9 | user details | admin | view current user details | to see what plot owners are currently in the system |  | 1 | 2 hours | Peter | 1 | Done | Medium | displays the plotowner's details: what plot they're on and their id etc.
2 | ban users | admin | banning permissions | ban users and/or plot owners |  | 2 | 2 hours | Luke | 9 | Done | Medium | given i "ban" a user, that users account is deleted and they are informed
11 | plot owner list of harvested crops and amount | plot owner | a list of all the crops ive harvested and how many of each i have | i can eventually put these up for sale on the shop |  | 2 | 5 hours | Adam |  | Done | Medium | given i harvest a crop, it appears in my harvested list or increments if the crop already exists
12 | plot owner sell items | plot owner | list items that have been planted to be sold | i can display available items from stock to be sold |  | 2 | 3 hours | Adam | 1 | Done | Medium | given I list an item, that item appears on the customer shop page | given I list an item, it is removed from harvested list and that item is unable to be listed again
13 | view available crop to purchase | customer | see all items on sale, their price and when they were grown/expire | i can view fresh friut and veg for home |  | 2 | 7 hours | Luke | 12 | Not started | Medium | all available items are shown to user
14 | put crops in basket | customer | i want to add items to basket | i can restock fruit and veg for home |  | 2 | 5 hours | Simon | 13 | Done | Medium | given I place an item in my basket, this item is temporarily removed from the shop | given I place an item in my basket, that item appears in my basket
15 | admin view sales records | admin | to be able to view a record of sales | to know what sells best |  | 2 | 4 hours | Peter | 14 | Done | Low | all previous sales are displayed to the admin | admin can view most popular vegetables
16 | approve/deny supply requests | admin | to be able to approve or deny plot owners request for supplies | I can help them grow crops or deny if i am unable to help | these are admin facilities | 2 | 5 hours | Peter | / | Done | Low | view current stock and supply of vegetables
17 | request supplies from admin | plot owner | to request supplies | keep the business going |  | 2 | 3 hours | Hannah | / | Done | Medium | given I request supplies, requested supplies are provided to me
18 | purchase basket and pick up in person | customer | click and collect i.e items from basket to be collected | there is no need to spend time searching in store | reduces stock for all purchased items | 2 | 5 hours | Simon | 18 | Done | Medium | given i purchase my basket, i am given a pickup time and date | given i purchase my basket, all items are removed from store permanently | given I purchase my basket, stock for purchased vegetables is reduced by the correct amount
19 | Encrypt passwords | user | to have my passwords encrypted | no one can hack into my account |  | 2 | 5 hours | Adam |  | Done | High | given i create an account, my password get stored in cipher text
20
21

## Data Validation
Status
Not started
In progress
Done
Priority
High
Medium
Low
Team Member Names
Name 1
Name 2
Name 3
Name 4
Name 5
Name 6
Name 7