## Sprint
[5 empty] | Start Date | 2024-03-04 |  |  | 2024-03-04 |  |  | 2024-03-05 |  |  | 2024-03-06 |  |  | 2024-03-07 |  |  | 2024-03-08 |  |  | 2024-03-11 |  |  | 2024-03-12 |  |  | 2024-03-13 |  |  | 2024-03-14 |  |  | 2024-03-15 |  |  | 2024-03-18 |  |  | 2024-03-19 |  |  | 2024-03-20 |  |  | 2024-03-21 |  |  | 2024-03-22 |  |  | 2024-03-25 |  |  | 2024-03-26 |  |  | 2024-03-27 |  |  | 2024-03-28 |  |  | 2024-03-29 |  |  | 2024-04-01 |  |  | 2024-04-02 |  |  | 2024-04-03 |  |  | 2024-04-04 |  |  | 2024-04-05 |  |  | 2024-04-08 |  |  | 2024-04-09 |  |  | 2024-04-10 |  |  | 2024-04-11 |  |  | 2024-04-12 |  |  | 2024-04-15 |  |  | 2024-04-16 |  |  | 2024-04-17 |  |  | 2024-04-18 |  |  | 2024-04-19 |  |  | 2024-04-22
[10 empty] | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 |  |  | Day 5 |  |  | Day 6 |  |  | Day 7 |  |  | Day 8 |  |  | Day 9 |  |  | Day 10 |  |  | Holiday 1 |  |  | Holiday 2 |  |  | Holiday 3 |  |  | Holiday 4 |  |  | Holiday 5 |  |  | Holiday 6 |  |  | Holiday 7 |  |  | Holiday 8 |  |  | Holiday 9 |  |  | Holiday 10 |  |  | Holiday 11 |  |  | Holiday 12 |  |  | Holiday 13 |  |  | Holiday 14 |  |  | Holiday 15 |  |  | Day 11 |  |  | Day 12 |  |  | Day 13 |  |  | Day 14 |  |  | Day 15 |  |  | Day 16 |  |  | Day 17 |  |  | Day 18 |  |  | Day 19 |  |  | Day 20 |  |  | Day 21
Worktype | Deliverable Area | Product Backlog Item or Group | Work item ID | Sprint Work item Description | Driver | Status | Pri | Initial | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Total Effort
Precondition / Debt |  |  | 1 | Create Customer Class | Adam | Complete | 2 | 4 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 2 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2
|  |  |  | Create Customer Class | Simon | Complete | 2.5 | 4 | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 2 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2
Tax |  |  | 2 | Fix bug in plant/water crop - needs to only allow user to update their plots not all plots (pass id into usermenu maybe?) | Adam | Complete | 0.5 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Story / Feature |  |  | 3 | Get login feature and any extras hooked up with csv files instead of dummy data | Hannah | Complete | 5 | 4 | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 2 | 4 | Pending | 2 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 4
Tax |  |  | 4 | move scanner code from admin to community garden | Peter | Complete | 1 | 1 | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0
Story / Feature |  |  | 5 | Test methods for every class - File access | Hannah | Complete | 4 | 4 | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 1 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 1 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2
|  |  |  | -Basic User | Adam | Complete | 2 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0.5 | 1.5 | Pending | 0 | 1.5 | Pending | 0 | 1.5 | Pending | 0 | 1.5 | Pending | 0 | 1.5 | In Progress | 0 | 1.5 | In Progress | 0 | 1.5 | In Progress | 0 | 1.5 | In Progress | 0.5 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0.5 | 0.5 | In Progress | 0.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0.5
|  |  |  | -Plot owner | Peter | Complete | 3 | 7 | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0
|  |  |  | -Test customer paired programming | Simon | complete | 4 | 2.5 | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 2 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 0.5 | Pending | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0 | 2 | In Progress | 0.5 | 1.5 | In Progress | 1.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2
|  |  |  | -Test customer paired programming | Adam | complete | 2 | 3 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 2 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 0 | 0.5 | In Progress | 2
|  |  |  | -Plot | Peter | Complete | 5 | 5 | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0
|  |  |  | -Crop | Simon | Complete | 3 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 3 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Story / Feature |  | PB Item 19 | 6 | Encrypt Passwords | Adam | Complete | 1 | 0.5 | 0 | 0.5 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0.5 | 0.5 | Pending | 0.5 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 1
Story / Feature |  | PB Item | 7 | Customer Login | Adam | Complete | 2 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 1 | 1 | In Progress | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Precondition / Debt |  |  | 8 | Create CSV for customers | Hannah | Complete | 5 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 3 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -code methods to write and read |  |  | 2 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0
Story / Feature |  | PB Item 7 | 9 | Track rain | Hannah | Complete | 1 | 1 | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -Code method to water all crops in system |  |  |  |  | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Story / Feature |  | PB Item 10 | 10 | Admin Banning menu | Peter | Complete | 3.5 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0
|  |  |  | Banned users can't login | Adam | Complete | 2 | 2 | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 0 | 2 | Pending | 2 | 0 | Complete | 1 | 0 | Complete | 1 | 0 | Complete | 1 | 0 | Complete | 1 | 0 | Complete | 1 | 0 | Complete | 1 | 0 | Complete | 0
Story / Feature |  | PB Item 8 | 11 | Admin Overview | Peter | Complete | 2 | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -view and create customers | Simon | Complete | 1 | 1 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -View contents and details of all plots |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Story / Feature |  | PB Item 11 | 12 | Plot owner Harvested Plots list | Adam | complete | 5 | 5 | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0.8 | 4.2 | In Progress | 0 | 4.2 | In Progress | 0.5 | 3.7 | In Progress | 0 | 3.7 | In Progress | 1 | 2.7 | In Progress | 0.5 | 2.2 | In Progress | 1 | 1.2 | In Progress | 0 | 1.2 | In Progress | 0 | 1.2 | In Progress | 0.2 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 1 | 2.2204e-16 | Complete | 0 | 2.2204e-16 | Complete | 0 | 2.2204e-16 | Complete | 0 | 2.2204e-16 | Complete | 0 | 2.2204e-16 | Complete | 0 | 2.2204e-16 | Complete | 0
|  |  |  | -Add attribute to plot owner that is a list of crops |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -Update harvest plot method to add to this list |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Precondition / Debt |  |  | 13 | Create CSV for marketplace | Hannah | Complete | 3 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 2 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 0 | 1 | In Progress | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 2
|  |  |  | -code methods to write and read |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Story / Feature |  | PB Item 12 | 14 | Plot owner sell harvested items | Adam | complete | 2.5 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 2.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Story / Feature |  | PB Item 12 | 14 | Plot owner sell harvested items | Simon | complete | 2.5 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 0 | 2.5 | Pending | 2.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -remove crop from harvested list |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -add crop to marketplace csv |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Story / Feature |  | PB Item 13 | 15 | Market Place main page | Luke | In Progress | 7 | 7 | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 7 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 7
|  |  |  | -add place to enter on main menu |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -read all items from marketplace csv |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | debug and tidy code | Simon | Complete | 3 | 2 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 2 | 1 | In Progress | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Story / Feature |  | PB Item 14 | 16 | Add crop to basket | Simon | Complete | 7.5 | 4 | 0 | 4 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 7.5 | Pending | 0 | 7.5 | Pending | 0 | 7.5 | Pending | 0 | 7.5 | Pending | 0 | 7.5 | Pending | 0 | 7.5 | Pending | 0 | 7.5 | Pending | 1.5 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 1 | 5 | In Progress | 5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -add crop to temporary basket record |  | Complete | 1 | 1 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Story / Feature |  | PB Item 18 | 17 | Purchase basket | Simon | Complete | 3 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 1.2 | 1.8 | In Progress | 0 | 1.8 | In Progress | 0 | 1.8 | In Progress | 0 | 1.8 | In Progress | 0 | 1.8 | In Progress | 0 | 1.8 | In Progress | 0 | 1.8 | In Progress | 1 | 0.8 | In Progress | 0.8 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -make all crops in basket sold |  | Complete | 1 | 1 | 0 | 1 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0.5 | 0.5 | In Progress | 0.5 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -Display message on screen to tell customer an order number and to pick up in person |  | Complete | 1 | 1 | 0 | 1 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 1 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
Story / Feature |  | PB Item 15 | 18 | Admin view sales records | Peter | Complete | 4 | 4 | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0
|  |  |  | -read all sold crops from marketplace csv |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -display all orders option |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -display total profit, amount of sales etc. |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Precondition / Debt |  |  | 19 | Create CSV for supply requests | Hannah | Complete | 5 | 5 | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 3 | 2 | In Progress | 2 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -code methods to write and read |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Story / Feature |  | PB Item 17 | 20 | Plot owner request supplies | Hannah | Complete | 3 | 3 | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 0 | 3 | Pending | 3 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0 | 0 | Complete | 0
|  |  |  | -Create menu of items to request |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -add request to CSV file |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
Story / Feature |  | PB Item 16 | 21 | Admin View requests | Peter | complete | 2 | 1 | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0 | 1 | Pending | 0
|  |  |  | -Read requests from CSV and Display |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -Add approve/deny options |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  |  | -Remove request from CSV if approved or denied |  |  |  | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
|  |  | 22 | Paperwork | Simon | Complete | 7 | 7 | 2 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 0 | 5 | In Progress | 4.5 | 0.5 | In Progress | 0.5 | 0 | Complete | 0 | 0 | Complete | 2
|  |  | 23 | Paperwork | Adam | Complete | 8 | 7 | 2 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 1 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0.5 | 3.5 | In Progress | 1 | 2.5 | In Progress | 0.5 | 2 | In Progress | 1.5 | 0.5 | In Progress | 1.5 | 0 | Complete | 0 | 0 | Complete | 3
|  |  | 24 | Paperwork | Hannah | Complete | 7 | 7 | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 2 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 1 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 2 | 2 | In Progress | 0 | 2 | In Progress | 2 | 0 | Complete | 3
|  |  | 25 | Paperwork | Peter | Complete | 7 | 7 | 2 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 0 | 5 | Pending | 1 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | Pending | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 0 | 4 | In Progress | 3
|  |  | 26 | Paperwork | Luke | In Progress | 7 | 7 | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 0 | 7 | Pending | 1 | 6 | Pending | 0 | 6 | Pending | 0 | 6 | Pending | 0 | 6 | Pending | 0 | 6 | Pending | 0 | 6 | Pending | 0 | 6 | Pending | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 0 | 6 | In Progress | 1
[7 empty] | 0 | 0 | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0 | 0 | Pending | 0
0
[9 empty] | Day |  | 1 | Day |  | 2 | Day |  | 3 | Day |  | 4 | Day |  | 5 | Day |  | 6 | Day |  | 7 | Day |  | 8 | Day |  | 9 | Day |  | 10 | Day |  | 11 | Day |  | 12 | Day |  | 13 | Day |  | 14 | Day |  | 15 | Day |  | 16 | Day |  | 17 | Day |  | 18 | Day |  | 19 | Day |  | 20 | Day |  | 21 | Day |  | 22 | Day |  | 23 | Day |  | 24 | Day |  | 25 | Day |  | 26 | Day |  | 27 | Day |  | 28 | Day |  | 29 | Day |  | 30 | Day |  | 31 | Day |  | 32 | Day |  | 33 | Day |  | 34 | Day |  | 35 | Day |  | 36
|  |  |  | Time Spent Mask |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0
|  |  |  | Time Left Mask |  |  |  |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0
|  |  |  | Status Mask |  |  |  |  | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
300 | 300 | 300 | 56A | Totals |  |  |  | 137 | 6 | 124 |  | 0 | 123.5 |  | 0 | 125.5 |  | 3 | 122.5 |  | 0 | 122.5 |  | 0 | 122.5 |  | 4 | 118.5 |  | 0.5 | 118 |  | 20.5 | 99.5 |  | 2.5 | 95 |  | 0 | 95 |  | 0 | 95 |  | 0 | 95 |  | 0 | 99 |  | 0 | 99 | 0 | 3 | 96 | 0 | 0 | 96 | 0 | 1.3 | 94.7 | 0 | 0 | 94.7 | 0 | 0.5 | 94.2 | 0 | 2.7 | 91.5 | 0 | 1.5 | 90 | 0 | 1 | 89 | 0 | 1.5 | 87.5 | 0 | 0 | 87.5 | 0 | 0 | 87.5 | 0 | 0.2 | 87.3 | 0 | 2 | 85.3 | 0 | 10.3 | 75.5 | 0 | 8.5 | 67 | 0 | 10 | 58 | 0 | 11 | 48 | 0 | 5.5 | 43.5 | 0 | 9 | 35.5 | 0 | 3 | 34.5 | 0 | 3 | 32.5 | 0
Formulas:
Status = (INDEX(Burndown,ROW([Status])-ROW(G3),MIN(TODAY()-SprintStart,29)*3+3))
Note on E6: Adam Greeran: This took a lot less time than anticipated. This was due to the previous development of the "currentPlotOwner" variable which is used to keep track of which user is logged in to the system at that moment.
Note on E33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adam and Simon will do this over pair programming over the next week

## Analysis
Working Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Date |  | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-22
Total Hours Remaining |  | 124 | 123.5 | 125.5 | 122.5 | 122.5 | 122.5 | 118.5 | 118 | 99.5 | 95 | 87.5 | 87.3 | 85.3 | 75.5 | 67 | 58 | 48 | 43.5 | 35.5 | 34.5 | #N/A
Hours Worked Today |  | 6 | 0 | 0 | 3 | 0 | 0 | 4 | 0.5 | 20.5 | 2.5 | 0 | 0.2 | 2 | 10.3 | 8.5 | 10 | 11 | 5.5 | 9 | 3 | #N/A
Total Hours Worked To Date |  | 6 | 6 | 6 | 9 | 9 | 9 | 13 | 13.5 | 34 | 36.5 | 36.5 | 36.7 | 38.7 | 49 | 57.5 | 67.5 | 78.5 | 84 | 93 | 96 | #N/A
Total Worked & Remaining Hours |  | 130 | 129.5 | 131.5 | 131.5 | 131.5 | 131.5 | 131.5 | 131.5 | 133.5 | 131.5 | 124 | 124 | 124 | 124.5 | 124.5 | 125.5 | 126.5 | 127.5 | 128.5 | 130.5 | #N/A
Average Hours Worked Per Day |  | 6 | 3 | 2 | 2.25 | 1.8 | 1.5 | 1.8571 | 1.6875 | 3.7778 | 3.65 | 1.4038 | 1.3593 | 1.3821 | 1.6897 | 1.9167 | 2.1774 | 2.4531 | 2.5455 | 2.7353 | 2.7429 | #N/A
Estimated Completion Date (Burndown) |  | 2024-03-24 16:00 | 2024-04-15 04:00 | 2024-05-07 18:00 | 2024-04-30 10:40 | 2024-05-15 01:20 | 2024-05-31 16:00 | 2024-05-14 19:23 | 2024-05-21 22:13 | 2024-04-09 08:07 | 2024-04-10 00:39 | 2024-06-09 07:53 | 2024-06-12 05:26 | 2024-06-10 17:11 | 2024-05-25 16:24 | 2024-05-16 22:57 | 2024-05-11 15:17 | 2024-05-05 13:36 | 2024-05-04 02:09 | 2024-04-30 23:29 | 2024-05-01 13:52 | #N/A
Estimated Completion Date (Task Completion) |  | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-03-04 | 2024-09-14 09:27 | 2024-09-21 21:49 | 2024-09-29 10:11 | 2024-11-07 | 2024-09-20 21:24 | 2024-09-08 18:44 | 2024-09-16 11:07 | 2024-09-06 | 2024-09-13 04:16 | 2024-08-16 02:11 | #N/A
Task Hours Pending |  | 124 | 123.5 | 125.5 | 122.5 | 122.5 | 122.5 | 118.5 | 118 | 99.5 | 95 | 50 | 50 | 50 | 44 | 39 | 31 | 23 | 22 | 22 | 22 | #N/A
Task Hours In Progress |  | 6 | 6 | 6 | 9 | 9 | 9 | 13 | 13.5 | 34 | 36.5 | 57.5 | 57.5 | 57.5 | 66 | 67 | 74 | 83 | 83 | 84 | 81 | #N/A
Task Hours Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5 | 16.5 | 16.5 | 14.5 | 18.5 | 20.5 | 20.5 | 22.5 | 22.5 | 27.5 | #N/A
Count of Workitems Pending |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 40 | 40 | 40 | 35 | 33 | 31 | 28 | 27 | 27 | 27 | #N/A
Count of Workitems In Progress |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 13 | 9 | 8 | 8 | 6 | 6 | 4 | #N/A
Count of Workitems Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 12 | 18 | 21 | 24 | 27 | 27 | 29 | #N/A
Workbook Settings |  | 2024-03-06: Comments
| SkipWeekends | 2024-03-04: 1; 2024-03-06: (0=30 calendar days; 1=30 working days). Set to 1 to have dates skip over weekends (30 working day sprint, >30 calendar day sprint). Do not switch after Sprint has started or data will be stored under wrong days
| DailyScrumDateModifier | 2024-03-04: 0; 2024-03-06: Number of days added to or subtracted from today's date to ensure the highlighted date column in the sprint worksheet corresponds to the day of the current daily Scrum meeting
Workbook-Wide Constants
| BurndownColumns | 2024-03-04: 3
HoursSpentColumn | bar: 2024-03-04
| HoursLeftColumn | 2024-03-04: 2
| StatusColumn | 2024-03-04: 3
Note on E41: Negative number to go back from today's date; positive number to go forward from today's date.

## Capacity
Current Date |  | Sun | 2024-04-21
Sprint Start Date |  | Mon | 2024-03-04
Sprint Tracking Statistics
Productive Hours = | 7 |  | Sprint Days = | 20 | time axis 2024-03-04 to 2024-04-21
|  |  | Scrum Team | %age of time on Project | Assigned Hours | [49 empty] | Available Hours | time axis 2024-03-04 to 2024-04-21
Total Remaining Hours: | 96 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
Total Capacity in Hours: | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
Variance in Hours: | 96 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | Simon | 100% | 29.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | Adam | 100% | 17.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | h | h | h | h | h |  |  | h | h | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | Hannah | 100% | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | Peter | 100% | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | Luke | 100% | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | v | v | v | v | v |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[6 empty] | v | = | Vacation & Public Holiday | [5 empty] | h | = | OOF (Sick, Biz Travel etc.) |  |  |  |  | h | = | OOF (Sick, Biz Travel etc.) |  |  |  |  | h | = | OOF (Sick, Biz Travel etc.) |  |  |  |  | h | = | OOF (Sick, Biz Travel etc.) |  |  |  |  | h | = | OOF (Sick, Biz Travel etc.) |  |  |  |  | h | = | OOF (Sick, Biz Travel etc.)

## Team Roster
Sprint Vision:
Sprint Team | Name | Alias | Primary Phone | Mobile Phone | Alternate Email | Instant Messaging
|  | . |  |  | .
| Simon Leckey | Simon | Phone | 7740038593 | scameronleckey02@qub.ac.uk | IM Information
| Adam Greeran | Adam | Phone | 7533244400 | agreeran01@qub.ac.uk | IM Information
| Hannah Dennis | Hannah | Phone | 7490814418 | hdennis02@qub.ac.uk | IM Information
| Peter Hepden | Peter | Phone | 7534720369 | phepden01@qub.ac.uk | IM Information
| Luke Mccall | Luke | 7495499119 | 7495499119 | lmccall09@qub.ac.uk | IM Information

## Project Specific Reports
Work Type Breakdown
Story / Feature | 16 | 72.73%
Tax | 2 | 9.091%
Precondition / Debt | 4 | 18.18%
Spike | 0 | 0%
Total | 22 | 100%
Functional Breakdown
Coding | 0 | #DIV/0!
Documentation | 0 | #DIV/0!
Testing | 0 | #DIV/0!
Project Mgt | 0 | #DIV/0!
Total | 0 | #DIV/0!
Work Item Status
Complete | 38 | 95%
In Progress | 2 | 5%
Pending | 0 | 0%
Postponed | 0 | 0%
Cancelled | 0 | 0%
Total | 40 | 100%